# Attachment F. Permitting & Development Milestones

# INTRODUCTION

All Applicants must provide a completed Attachment F. Permitting & Development Milestones as part of their Application Submission. This attachment will remain confidential.

# Form Usage

Applicants must utilize this attachment as a form, providing information in the response space provided. Applicants may append any necessary information if needed. The final version of Attachment F must be submitted as a PDF file with the Application.

# Permitting Plan

## List and Description of Necessary Permits & Approvals

A complete and comprehensive list and description of all the permits, licenses or environmental assessments or impact statements (e.g., state and local) that the Project must receive prior to construction and operation. The responsible agency for issuing approvals must be identified.

## Permitting and Assessment Status

The status of the Applicant’s permits, licenses and environment assessments or impact statements, along with expected timelines for achieving any outstanding approvals, must be identified. Applicants should provide documentation of approval or evidence of drafted or submitted documents to support the Applicant’s claims.

## Permitting Risk

Any risks in permitting or licensing delays shall be identified along with the Applicant's plan to mitigate and/or remedy these risks where possible. This may include any energy storage moratoria or otherwise restrictive local laws.

## Permitting Timeline

Details on how the permitting and licensing timeline is reasonable and supports the Project achieving its proposed Commercial Operation Date, within the requirements detailed in Section 2.2 Eligibility Requirements.

## Applicable Desktop or Field Studies

A summary and/or other evidentiary documentation that details the status of any applicable desktop or field studies needed for the Project’s development, construction, or operations.

## Measures for Sensitives Habitats and Protected Species

A summary of any known and anticipated measures to avoid or minimize impacts on sensitive habitats and protected species.

# Key Development Milestones

## Critical Path Schedule

Show a critical path schedule of the project development, permitting, equipment procurement, financing, and construction indicating the different length of time each phase will take, when they are scheduled to be completed and the proposed Commercial Operation Date of the energy storage Project. An Applicant should provide sufficient information and adequate documentation to demonstrate that the Project has a reasonable plan and sufficient time to achieve the anticipated Commercial Operation Date.

## Commercial Operation Date

Provide the proposed Commercial Operate Date of the Project.

All Projects seeking an award must be capable of achieving commercial operation within 24 months after a Project is approved by the Commission (i.e., October 1, 2028), except where the Applicant is able to demonstrate that achieving this Commercial Operation Date is not possible for Good Cause Shown, in which case the Project has the ability to achieve commercial operation within 36 months after the Project is selected by the Commission.

## Good Cause Shown Conditions

If an Applicant is offering a proposed Commercial Operation Date that is more than 24 months after a Project would be approved by the Commission (i.e., October 1, 2028), an Applicant should describe in detail the which Good Cause Shown Conditions apply to the Project and how they impact the critical path schedule (i.e., reasons for schedule extension, expected delay to schedule, risks associated, etc.).

The following activities will be considered by the Commission in determining Good Cause Shown for a schedule extension:

1.	PJM’s interconnection process;

2.	the issuance of permits;

3.	delivery of critical Project components with long lead times; and

4.	utility construction of interconnection facilities and network upgrades.

## Reasonableness of Timeline

An Applicant should opine on how the anticipated timelines and key development milestones enable the energy storage Project to achieve the proposed Commercial Operation Date.

## Procurement Plan

The status of the Applicant’s procurement plan, including procurement and delivery of all major equipment to construct the Project, inclusive of any equipment that has previously been purchased or contracted for the Project. If no major equipment has been purchased or contracted, Applicants should include a plan to procure all the major components, including equipment from Original Equipment Manufacturers (OEMs), relevant communications with OEMs, estimated lead time for delivery of Project components to the site and any quotes/pricing received from OEMs for the Project components.

## Attestation to Schedule Extension Conditions

An Applicant shall provide attestation that it understands the following conditions related to Schedule Extension and Good Cause Shown Conditions.